Grundtvig Multilateral project 2009 - 2011: LOAC – Learning outcome of Amateur Culture

21.11.2010 / hjv

Adopted at the third partner meeting

LOAC, task plan 2009 – 2011, revised 21.11.2010

Reason for change of time table of the task plan from Nov 2009:

- We could need more time for the work in the second phase (to develop the two tools and prepare the compendia on best practise, and we could need more time for announcements of the pilot courses in the third phase.

- It means we should expand the periods of the second phase to Feb 2011 and expand the period of the third phase to June 2011.

- Then we still keep the time schedule for the Fourth phase with dissemination in Aug 2011 and the fifth phase with exploitation from Aug to Nov 2011.

- We move the fourth partner meeting from the end of the third phase to the Mid of the fifth phase with focus on adjustment of exploitation activities and project evaluation.

# Task plan: Short version - revised

First phase: Documentation survey and guidelines for tools, Oct 2009 – June 2010

- The first partnership meeting, Medio December 2009 in Denmark

- Survey on learning qualities and outcome, Dec. 2009  – May 2010

- Guidelines for two tools of valuation, May – June 2010

- Second phase: Develop tools for valuation, June – October 2010

- The second partnership Meeting, June 2010 in Nederland

- Develop the pilot valuation tool of personal learning, June 2010– Feb 2011

- Develop the pilot valuation tool of organizational learning, June 2010  – Feb 2011

- Prepare compendia on best practise, June 2010 – Feb 2011

- Third Phase: Develop and complete four pilot courses, October 2010 – March 2011

- The third partnership meeting, November 2010 in Slovenia

- Develop and complete a 6days pilot Grundtvig in-training course, Nov. 2010- June 2011

- Develop and complete a 6days pilot Grundtvig workshop course, Nov. 2010 – June 2011

- Forth phase: Dissemination of the results of the project, March 2011 – July 2011

- Publish: Report of qualities, Compendia of best practise, Course compendia, April – July 2011

- Mount four valuation tools of personal learning, April – July 2011

- Mount four valuation tools of organizational learning, April – July 2011

- Fifth phase: Exploitation of the results of the project, August 2011 – November 2011

- Prepare four conferences in each country, Aug – Oct 2011

- Complete four conferences in each country, October 2011

- 11.  The fourth partner meeting, Oct 2011

- Multiplication and mainstreaming of the projects result, Sep – Nov 2011

- Project report and account, November 2011

- All phases: Monitoring, QU, management and coordination, October 2009 – November 2011

- Monitoring and quality assurance, Oct. 2009 – Nov. 2011

- Management and coordination, Oct. 209 – Nov. 2011

| Time table and work packet, Revised 21.11.2010 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Partner Meetings |  |  |  |  |  |  |  | P |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Development Work |  |  |  |  |  |  |  | W |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | U |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Dissemination |  |  |  |  |  |  |  | D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |
|  | LOAC, Grundtvig multilateral project, October 2009 - November 2011 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Exploitation |  |  |  |  |  |  |  | E |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | L |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Management |  |  |  |  |  |  |  | M |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | F |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Quality Plan |  |  |  |  |  |  |  | Q |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase | Work packet | Title | 2009 |  |  |  |  |  |  | 2010 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2011 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | Sept |  | Oct | Nov |  | Dec |  | Jan |  | Feb | Mar |  |  | April |  | May | Jun |  |  | July | Aug |  | Sept |  | Oct | Nov |  | Dec |  | Jan |  | Feb | Mar | April |  | May | June |  |  | July |  | Aug |  | Sept |  | Okt | Nov |  | Dec |  |  |  |  |  |  |  |  |  |  |
| I | 1 | First meeting, Medio Dec, Copenhagen |  |  | p | p |  | P |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Survey of learning outcome and report |  |  |  |  |  | W |  | W |  | W | W |  |  | W |  | W |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 | Guidelines for two tools |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | W | W |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| II | 4 | Second meeting, June 2010 in Holland |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | p | P |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 5 | Develop pilot tool, personal learning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | W |  |  | W | W |  | W |  | W | W |  | W |  | W |  | W |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6 | Develop pilot tool, org. learning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | W |  |  | W | W |  | W |  | W | W |  | W |  | W |  | W |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 7 | Prepare compendia best practise |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | W |  |  | W | W |  | W |  | W | W |  | W |  | W |  | W |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| III | 8 | Third meeting, Nov 2010 in Slovenia |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | p | P |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 9 | Pilot course, Grundtvig in-training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | W |  | W |  | W |  | W | W | W |  | W | W |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 10 | Pilot course, Grundtvig Workshop |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | W |  | W |  | W |  | W | W | W |  | W | W |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| IV | 11 | Fourth meeting, Oct in Denmark |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | p |  |  | p |  | p |  | p |  | P |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 12 | Prepare and publish three reports |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | W |  |  | W |  | D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 13 | Mount four tools of personal learning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | W |  |  | W |  | D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 14 | Mount four tools of org. learning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | W |  |  | W |  | D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| V | 15 | Prepare four conferences |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | d |  | d |  | D |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 16 | Complete four conferences |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | D |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 17 | Multiplication & mainstreaming |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | E |  | E | E |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 18 | Project report & account |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Q | M |  |  |  |  |  |  |  |  |  |  |  |  |
| All | 19 | Management & account |  |  | M | M |  | M |  | M |  | M | M |  |  | M |  | M | M |  |  | M | M |  | M |  | M | M |  | M |  | M |  | M | M | M |  | M | M |  |  | M |  | M |  | M |  | M | M |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 20 | Quality assurance & Coordination |  |  | Q | Q |  | Q |  | Q |  | Q | Q |  |  | Q |  | Q | Q |  |  | Q | Q |  | Q |  | Q | Q |  | Q |  | Q |  | Q | Q | Q |  | Q | Q |  |  | Q |  | Q |  | Q |  | Q | Q |  |  |  |  |  |  |  |  |  |  |  |  |